## Sheet1
Unit Testing Case Summary
Project Type |  |  | bug |  |  | Run | Act | Act | Test
| Test suite | Status | IDs | Description | Risk Priority Number(1-10) | By | Date | Effort (hours) | Duration(mins)
Backend | Sales Dashboard Collection | done |  |  |  | Tester01 | 2024-11-18 | 3 | 45
Backend | Admin Dashboard Collection | done |  |  |  | Tester01 | 2024-11-19 | 2.5 | 40
Backend | Warehouse Manager Dashboard Collection | done |  |  |  | Tester02 | 2024-11-20 | 4 | 50
Database | Database | done |  |  |  | Tester01 | 2024-11-18 | 3 | 35

## Sheet2
Integration Testing Case Summary
Project Type |  | bug |  |  | Run | Act | Act | Test
Test Suite | Status | IDs | Description | Risk Priority Number(1-10) | By | Date | Effort (hours) | Duration(mins)
Warehouse Manager Functionalities | done | BUG3.1 | website crashed upon clicking button | 10 | Tester01 | 2024-11-18 | 4 | 50
| done | BUG3.2 | Item names can be added with types other than string | 10 | Tester02 | 2024-11-19 | 3.5 | 45
| done | BUG3.3 | Item quantities can be added with values less than 0 | 5 | Tester01 | 2024-11-20 | 3.5 | 40
System Administrator Functionalities | done | BUG3.4 | website crashed upon clicking button | 5 | Tester02 | 2024-11-20 | 4 | 40
Sales Staff Functionalities | done | BUG3.5 | website crashed upon clicking button | 10 | Tester01 | 2024-11-21 | 3.5 | 50

## Sheet3
System Testing Case Summary
Project Type |  | bug |  |  | Run | Act | Act | Test
Test Suite | Status | IDs | Description | Risk Priority Number(1-10) | By | Date | Effort (hours) | Duration(mins)
Customer Service APIs | done | BUG2.1 | website crashed upon clicking button | 10 | Tester01 | 2024-11-18 | 4 | 50
Inventory Service APIs | done | BUG2.2 | website crashed upon clicking button | 10 | Tester02 | 2024-11-19 | 3.5 | 40
| done | BUG2.3 | Item names can be added with types other than string | 5 | Tester02 | 2024-11-20 | 3 | 35
| done | BUG2.4 | Item quantities can be added with values less than 0 | 5 | Tester01 | 2024-11-21 | 4 | 45
Users Service APIs | done | BUG2.5 | website crashed upon clicking button | 10 | Tester01 | 2024-11-21 | 3.5 | 40

## Sheet4
Unsolved defects
Product Risk Areas | Number of Unsolved Defects | Percentage
Performance, Load | 3 | 18%
Functionality, Data | 2 | 15%
Interface | 3 | 13%